## RICs
ID | Description | Type | Date Identified | Impact | Probability | Importance | Response | Owner | Closure Date
1 | A group member falling ill/not turning up to group meeting | Risk | 2020-01-16 | 100 | High | 65 | Request that the team member explains why they didn't show up or how badly ill they are. | Fraser Yuill
2 | Data Loss | Risk | 2020-01-23 | 300 | Low | 90 | Create backups of all important information including any info given to us and ain info we create. | Fraser Yuill
3 | Hardware/software failure | Risk | 2020-01-23 | 300 | Low | 90 | Use other machine and/or use facilities at Napier. | Fraser Yuill
4 | Dismissal of team member | Risk | 2020-01-30 | 400 | Very Low | 40 | Make sure that all team members are working equally and efficiently and make sure to consider and keep record of any and all complaints by any member. If a member is dismissed then change around the planned strategy to adapt to their loss. | Fraser Yuill
5 | Loss of confidential information | Risk | 2020-01-30 | 400 | Low | 120 | Create a sort of failsafe that will insure that the confidential information is not misplaced. | Fraser Yuill
6 | Member contracting the Corona Virus | Risk | 2020-03-16 | 400 | Low | 120 | Tell member to stay at home and do any work that they can without pushing them too much. | Fraser Yuill
7 | Analysis of effectiveness of PDTs changed to talking to other students and will be conducted in March. | Change | 2020-02-04 | 50 |  | 50 | Change approach and adapt to new time date, gives us a better idea of what students think of the PDT system. | Fraser Yuill